## General
D365 BC Estimate: Prepared for Aptean
Technology | Business Central (BC)
Role | TA - Technical Architect
Task | Estimate
Project | Aptean
Requestor | Inida Noga
Service Lead | eugene.tsuprenko@ciellos.com
EVERYTHING DYNAMICS BUILD | UPGRADE| SUPPORT

## Estimate (1)
D365 BC Estimate: Prepared for Aptean (Otis McAllister)
# | Task | Description | Who | State | SA | PM | FC | AS | TA | SE/DevOps | DEV | ESTIMATE (Hrs) | Price (USD)
Scope Work Breakdown Structure
01 | ASSESS
01.01 | Analysis, Preliminary Preparation | Requirements Analysis, Sessions with Customer | Ciellos | Execute |  |  |  |  | 16 |  |  | 16 | 1600
01.02 | Project Organizationand Planning, Communication, Scheduling, Execution |  | Ciellos | Execute |  | 4 | [5 empty] | 4 | 400
02 | DESIGN
02.01 | System Engineering | [10 empty] | 0 | 0
02.01.01 | Installation, configuration Test & Dev Environments | Installation and configuration the requiered version of Business Central on customer side for developing and testing purposes | Ciellos | Execute | [5 empty] | 8 |  | 8 | 800
02.01.02 | Installation, configuration Upgrade Environment | Installation and configuration versions (Dynamics NAV 2018, Business Central 140, the latest version what will be used in Data Migration. | Ciellos | Execute | [5 empty] | 8 |  | 8 | 800
02.01.03 | Configure DevOps Management Environment | Configure DevOps Source Code Repositories and Azure DevOps | Ciellos | Execute | [5 empty] | 4 |  | 4 | 400
02.02 | Solution Architecture | Functionality analysis to determine what needs to be migrated. Configuring migration tools. | [9 empty] | 0 | 0
02.02.01 | Defining data for migration and preliminary steps before upgrade | - Defining what should be upgraded: companies, functionality, logs, etc. - Defining preliminary steps: data compression, deleting unnecessary data (change log, etx.) - Defining upgrade policy for administrative data: users, permissions, personnalisations, reports, job queues, web services, etc. - Defining upgrade of integration with Microsoft and 3rd party systems: Azure Entra, Power BI, API OAuth 2.0, Dynamics 365 | Ciellos | Execute |  |  |  |  | 8 |  |  | 8 | 800
02.02.02 | Defining data upgrade policy for Aptean extensions (applications) | Defining how and what data should be migrated for each extension. | Ciellos | Execute |  |  |  |  | 4 |  |  | 4 | 400
02.02.03 | Mapping tables (fields) between modules and applications | Since we have one module related to many applications, we need to create mapping between them | Ciellos | Execute |  |  |  |  | 24 |  |  | 24 | 2400
02.02.04 | Defining data upgrade policy for other ISV products | Defining what extensions should be migrated. Defining how and what data should be migrated for each extension. | Ciellos | Execute |  |  |  |  | 4 |  |  | 4 | 400
02.02.05 | Defining tables and/or fields should not be upgraded | Defining which data will be migrated indirectly, for example by configuration packages, XML port, mannual input, etc. | Ciellos | Execute |  |  |  |  | 8 |  |  | 8 | 800
02.02.06 | Defining tables and fields mapping | Defining tables and fields mapping | Ciellos | Execute |  |  |  |  | 8 |  |  | 8 | 800
02.02.07 | Configuring upgrade tools. | Configure (Create) SQL scripts, Powershell scripts, etc. used in upgrading the data | Ciellos | Execute |  |  |  |  | 16 |  |  | 16 | 1600
| Project Organization, Communication, Execution |  | Ciellos | Execute |  | 8 | [5 empty] | 8 | 800
0
0
03 | BUILD | [11 empty] | 0
03.01 | Upgrading the Application Code | [10 empty] | 0 | 0
03.01.06 | CST Code Upgrade (Redesign) - Tables |  | Ciellos | Execute |  |  |  |  | 19.05 |  | 127 | 146.05 | 14605
03.01.07 | CST Code Upgrade (Redesign) - Pages |  | Ciellos | Execute |  |  |  |  | 19.8 |  | 132 | 151.8 | 15180
03.01.08 | CST Code Upgrade (Redesign) - Codeunits |  | Ciellos | Execute |  |  |  |  | 12.3 |  | 82 | 94.3 | 9430
03.01.09 | CST Code Upgrade (Redesign) - Reports |  | Ciellos | Execute |  |  |  |  | 17.4 |  | 116 | 133.4 | 13340
03.01.10 | CST Code Upgrade (Redesign) - Others |  | Ciellos | Execute |  |  |  |  | 4.5 |  | 30 | 34.5 | 3450
03.02 | Upgrade the data: First Run | [10 empty] | 0 | 0
03.02.01 | Reducing the amount of data for upgrade | Reducing the amount of data in the areas defined in task 02.02 - Delete data in unused tables: Change Log Entry, Integration Records, etc. - Compress data in NAV 2018 (G/L Entry, Value Entry, Customer Ledger Entry, etc.) where it is possible - Other tasks defined in task 02.02 | Ciellos | Execute |  |  |  |  | 2.4 |  | 16 | 18.4 | 1840
03.02.02 | Upgrade to BC140 Dynamics 365 Business Central Spring 2019 |  | Ciellos | Execute |  |  |  |  | 2.4 |  | 16 | 18.4 | 1840
03.02.03 | Upgrade to BC220 Dynamics 365 Business Central 2023 release wave 1 |  | Ciellos | Execute |  |  |  |  | 2.4 |  | 16 | 18.4 | 1840
03.02.04 | Post-upgrade tasks |  | Ciellos | Execute |  |  |  |  | 1.2 |  | 8 | 9.2 | 920
03.02.05 | Configuration, personnalisations and other administrative tasks | Configuration, personnalisations, administrative tasks in Test Environment | Ciellos | Execute |  |  |  |  | 0.6 |  | 4 | 4.6 | 460
03.04 | Demo and Training |  | Aptean | Execute
03.05 | UAT support and Stabilization |  | Ciellos | Execute |  |  |  |  | 6 |  | 24 | 30 | 3000
03.06 | Upgrade the data: Dry Run |  | Ciellos | Execute | [7 empty] | 0 | 0
03.06.01 | Reducing the amount of data for upgrade |  | Ciellos | Execute |  |  |  |  | 1 |  | 8 | 9 | 900
03.06.02 | Upgrade to BC140 Dynamics 365 Business Central Spring 2019 |  | Ciellos | Execute |  |  |  |  | 1 |  | 8 | 9 | 900
03.06.03 | Upgrade to BC220 Dynamics 365 Business Central 2023 release wave 1 |  | Ciellos | Execute |  |  |  |  | 1 |  | 8 | 9 | 900
03.06.04 | Post-upgrade tasks |  | Ciellos | Execute |  |  |  |  | 1.2 |  | 4 | 5.2 | 520
03.06.05 | Configuration, personnalisations and other administrative tasks | Configuration, personnalisations, administrative tasks in Test Environment | Ciellos | Execute |  |  |  |  | 0.6 |  | 2 | 2.6 | 260
| Project Organization, Communication, Execution |  | Ciellos | Execute |  | 40 | [5 empty] | 40 | 4000
0
0
04 | DEPLOY | [11 empty] | 0
04.01 | Installation, configuration Production Environment | Installation and configuration production environment | Ciellos | Execute |  |  |  |  | 4 | 16 |  | 20 | 2000
04.02 | Data migration: Go-Live | [10 empty] | 0 | 0
04.02.01 | Reducing the amount of data for upgrade |  | Ciellos | Execute |  |  |  |  | 2 |  | 8 | 10 | 1000
04.02.02 | Upgrade to BC140 Dynamics 365 Business Central Spring 2019 |  | Ciellos | Execute |  |  |  |  | 2 |  | 8 | 10 | 1000
04.02.03 | Upgrade to BC220 Dynamics 365 Business Central 2023 release wave 1 |  | Ciellos | Execute |  |  |  |  | 2 |  | 8 | 10 | 1000
04.02.04 | Post-upgrade tasks |  | Ciellos | Execute |  |  |  |  | 2 |  | 8 | 10 | 1000
04.02.05 | Configuration, personnalisations and other administrative tasks in Test Environment |  | Ciellos | Execute |  |  |  |  | 2 |  | 8 | 10 | 1000
04.03 | Post-upgrade support |  | Ciellos | Execute |  |  |  |  | 8 |  | 40 |  | 4800
| Project Organization, Communication, Execution |  | Ciellos | Execute |  | 16 | [5 empty] | 16 | 1600
| Total Estimate (Time and Materials) |  |  |  | 0 | 68 | 0 | 0 | 202.85 | 36 | 681 | 987.85 | 98785
Role Description | Role |  |  | Rate ($/Hr) | # | Price ($) | Notes and Assumptions
| Solution Architect | SA |  | 100 | 0 | 0 | Prerequisites - Aptean developer license for BC14 and BC22 - Modules 37046310 bcEDI & bcPacknShip, 37084500 bcERP - source code, BC130 (BC140) - Aptean extensions, version BC22 - app file, source code File with mappings - from module "bcEDI & bcPacknShip" to application "Aptean EDIAptean" - from module "37084500 bcERP" to Aptean Applications - access to test & dev environment - access to upgrade environment Deliverables - Installed and configured environments: dev, test, production - Customer extension (includes customisations to Microsoft & Aptean apps) - Source Code & app - Upgraded to BC 22 databases: dev, test & production Out of Scope Items not listed as Ciellos tasks are not in scope. Risks This estimate may vary once the test migration is started.
| Project Manager | PM |  | 100 | 1 | 6800
| Functional Consultant | FC |  | 100 | 0 | 0
| Application Specialist | AS |  | 100 | 0 | 0
| Technical Architect | TA |  | 100 | 1 | 20285
| Systems Engineer / DevOps | SE/DevOps |  | 100 | 1 | 3600
| Development | DEV |  | 100 | 1 | 68100
Total Assigned Staff (Individual Contributors) |  |  |  |  | 4 | 98785
Project Duration (Months) |  |  |  |  | 2
EVERYTHING DYNAMICS BUILD | UPGRADE| SUPPORT

## Estimate (2)
D365 BC Estimate: Prepared for Aptean (Otis McAllister)
# | Task | Description | Who | State | SA | PM | FC | AS | TA | SE/DevOps | DEV | ESTIMATE (Hrs) | Price (USD)
Scope Work Breakdown Structure
01 | ASSESS
01.01 | Analysis, Preliminary Preparation | Requirements Analysis, Sessions with Customer | Ciellos | Execute |  |  |  |  | 16 |  |  | 16 | 1600
01.02 | Project Organizationand Planning, Communication, Scheduling, Execution |  | Ciellos | Execute |  | 4 | [5 empty] | 4 | 400
02 | DESIGN
02.01 | System Engineering | [10 empty] | 0 | 0
02.01.01 | Installation, configuration Test & Dev Environments | Installation and configuration the requiered version of Business Central on customer side for developing and testing purposes | Aptean | Execute | [7 empty] | 0 | 0
02.01.02 | Installation, configuration Upgrade Environment | Installation and configuration versions (Dynamics NAV 2018, Business Central 140, the latest version what will be used in Data Migration. | Aptean | Execute | [7 empty] | 0 | 0
02.01.03 | Configure DevOps Management Environment | Configure DevOps Source Code Repositories and Azure DevOps | Ciellos | Execute | [5 empty] | 4 |  | 4 | 400
02.02 | Solution Architecture | Functionality analysis to determine what needs to be migrated. Configuring migration tools. | [9 empty] | 0 | 0
02.02.01 | Defining data for migration and preliminary steps before upgrade | - Defining what should be upgraded: companies, functionality, logs, etc. - Defining preliminary steps: data compression, deleting unnecessary data (change log, etx.) - Defining upgrade policy for administrative data: users, permissions, personnalisations, reports, job queues, web services, etc. - Defining upgrade of integration with Microsoft and 3rd party systems: Azure Entra, Power BI, API OAuth 2.0, Dynamics 365 | Ciellos | Execute |  |  |  |  | 8 |  |  | 8 | 800
02.02.02 | Defining data upgrade policy for Aptean extensions (applications) | Defining how and what data should be migrated for each extension. | Ciellos | Execute |  |  |  |  | 4 |  |  | 4 | 400
02.02.03 | Mapping tables (fields) between modules and applications | Since we have one module related to many applications, we need to create mapping between them | Ciellos | Execute |  |  |  |  | 24 |  |  | 24 | 2400
02.02.04 | Defining data upgrade policy for other ISV products | Defining what extensions should be migrated. Defining how and what data should be migrated for each extension. | Ciellos | Execute |  |  |  |  | 4 |  |  | 4 | 400
02.02.05 | Defining tables and/or fields should not be upgraded | Defining which data will be migrated indirectly, for example by configuration packages, XML port, mannual input, etc. | Ciellos | Execute |  |  |  |  | 8 |  |  | 8 | 800
02.02.06 | Defining tables and fields mapping | Defining tables and fields mapping | Ciellos | Execute |  |  |  |  | 8 |  |  | 8 | 800
02.02.07 | Configuring upgrade tools. | Configure (Create) SQL scripts, Powershell scripts, etc. used in upgrading the data | Ciellos | Execute |  |  |  |  | 16 |  |  | 16 | 1600
| Project Organization, Communication, Execution |  | Ciellos | Execute |  | 8 | [5 empty] | 8 | 800
0
0
03 | BUILD | [11 empty] | 0
03.01 | Upgrading the Application Code | [10 empty] | 0 | 0
03.01.06 | CST Code Upgrade (Redesign) - Tables |  | Ciellos | Execute |  |  |  |  | 19.05 |  | 127 | 146.05 | 14605
03.01.07 | CST Code Upgrade (Redesign) - Pages |  | Ciellos | Execute |  |  |  |  | 19.8 |  | 132 | 151.8 | 15180
03.01.08 | CST Code Upgrade (Redesign) - Codeunits |  | Ciellos | Execute |  |  |  |  | 12.3 |  | 82 | 94.3 | 9430
03.01.09 | CST Code Upgrade (Redesign) - Reports |  | Ciellos | Execute |  |  |  |  | 17.4 |  | 116 | 133.4 | 13340
03.01.10 | CST Code Upgrade (Redesign) - Other Objects |  | Ciellos | Execute |  |  |  |  | 4.5 |  | 30 | 34.5 | 3450
03.02 | Upgrade the data: First Run | [10 empty] | 0 | 0
03.02.01 | Reducing the amount of data for upgrade | Reducing the amount of data in the areas defined in task 02.02 - Delete data in unused tables: Change Log Entry, Integration Records, etc. - Compress data in NAV 2018 (G/L Entry, Value Entry, Customer Ledger Entry, etc.) where it is possible - Other tasks defined in task 02.02 | Ciellos | Execute |  |  |  |  | 2.4 |  | 16 | 18.4 | 1840
03.02.02 | Upgrade to BC140 Dynamics 365 Business Central Spring 2019 |  | Ciellos | Execute |  |  |  |  | 2.4 |  | 16 | 18.4 | 1840
03.02.03 | Upgrade to BC220 Dynamics 365 Business Central 2023 release wave 1 |  | Ciellos | Execute |  |  |  |  | 2.4 |  | 16 | 18.4 | 1840
03.02.04 | Post-upgrade tasks |  | Ciellos | Execute |  |  |  |  | 1.2 |  | 8 | 9.2 | 920
03.02.05 | Configuration, personnalisations and other administrative tasks | Configuration, personnalisations, administrative tasks in Test Environment | Ciellos | Execute |  |  |  |  | 0.6 |  | 4 | 4.6 | 460
03.04 | Demo and Training |  | Aptean | Execute
03.05 | UAT support and Stabilization |  | Ciellos | Execute |  |  |  |  | 6 |  | 24 | 30 | 3000
03.06 | Upgrade the data: Dry Run |  | Ciellos | Execute | [7 empty] | 0 | 0
03.06.01 | Reducing the amount of data for upgrade |  | Ciellos | Execute |  |  |  |  | 1 |  | 8 | 9 | 900
03.06.02 | Upgrade to BC140 Dynamics 365 Business Central Spring 2019 |  | Ciellos | Execute |  |  |  |  | 1 |  | 8 | 9 | 900
03.06.03 | Upgrade to BC220 Dynamics 365 Business Central 2023 release wave 1 |  | Ciellos | Execute |  |  |  |  | 1 |  | 8 | 9 | 900
03.06.04 | Post-upgrade tasks |  | Ciellos | Execute |  |  |  |  | 1.2 |  | 4 | 5.2 | 520
03.06.05 | Configuration, personnalisations and other administrative tasks | Configuration, personnalisations, administrative tasks in Test Environment | Ciellos | Execute |  |  |  |  | 0.6 |  | 2 | 2.6 | 260
| Project Organization, Communication, Execution |  | Ciellos | Execute |  | 40 | [5 empty] | 40 | 4000
0
0
04 | DEPLOY | [11 empty] | 0
04.01 | Installation, configuration Production Environment | Installation and configuration production environment | Aptean | Execute | [7 empty] | 0 | 0
04.02 | Data migration: Go-Live | [10 empty] | 0 | 0
04.02.01 | Reducing the amount of data for upgrade |  | Ciellos | Execute |  |  |  |  | 2 |  | 8 | 10 | 1000
04.02.02 | Upgrade to BC140 Dynamics 365 Business Central Spring 2019 |  | Ciellos | Execute |  |  |  |  | 2 |  | 8 | 10 | 1000
04.02.03 | Upgrade to BC220 Dynamics 365 Business Central 2023 release wave 1 |  | Ciellos | Execute |  |  |  |  | 2 |  | 8 | 10 | 1000
04.02.04 | Post-upgrade tasks |  | Ciellos | Execute |  |  |  |  | 2 |  | 8 | 10 | 1000
04.02.05 | Configuration, personnalisations and other administrative tasks in Test Environment |  | Ciellos | Execute |  |  |  |  | 2 |  | 8 | 10 | 1000
04.03 | Post-upgrade support |  | Ciellos | Execute |  |  |  |  | 8 |  | 40 |  | 4800
| Project Organization, Communication, Execution |  | Ciellos | Execute |  | 16 | [5 empty] | 16 | 1600
| Total Estimate (Time and Materials) |  |  |  | 0 | 68 | 0 | 0 | 198.85 | 4 | 681 | 951.85 | 95185
Role Description | Role |  |  | Rate ($/Hr) | # | Price ($) | Notes and Assumptions
| Solution Architect | SA |  | 100 | 0 | 0 | Prerequisites - Aptean developer license for BC14 and BC22 - Modules 37046310 bcEDI & bcPacknShip, 37084500 bcERP - source code, BC130 (BC140) - Aptean extensions, version BC22 - app file, source code File with mappings - from module "bcEDI & bcPacknShip" to application "Aptean EDIAptean" - from module "37084500 bcERP" to Aptean Applications - access to configured test & dev environment - access to configured upgrade environmentnt Deliverables - Installed and configured environments: dev, test, production - Customer extension (includes customisations to Microsoft & Aptean apps) - Source Code & app - Upgraded to BC 22 databases: dev, test & production Out of Scope Items not listed as Ciellos tasks are not in scope. Risks This estimate may vary once the test migration is started.
| Project Manager | PM |  | 100 | 1 | 6800
| Functional Consultant | FC |  | 100 | 0 | 0
| Application Specialist | AS |  | 100 | 0 | 0
| Technical Architect | TA |  | 100 | 1 | 19885
| Systems Engineer / DevOps | SE/DevOps |  | 100 | 1 | 400
| Development | DEV |  | 100 | 1 | 68100
Total Assigned Staff (Individual Contributors) |  |  |  |  | 4 | 95185
Project Duration (Months) |  |  |  |  | 2
EVERYTHING DYNAMICS BUILD | UPGRADE| SUPPORT

## Setup (hidden)
Technology | Role | Task | Project | Requestor | Service Lead
Business Central (BC) | SA - Solution Architect | Pre-sale | Cavallo - Ad Hoc Support | Sarah Harper | eugene.tsuprenko@ciellos.com
Finance and Supply Chain Management (FSC) | FC - Functional Consultant | Assessment | Coss - BC Product Development | Natalie Reichstein | kseniia.golovan@ciellos.com
Sales (CRM, CE, Dataverse) | AS - Application Specialist | Workshop | Flavor Materials - Ad Hoc | Anatolii Razgoniaiev | kim.klausen@ciellos.com
Power Platform | TA - Technical Architect | Estimate | Lakeshore Consulting - CF Packing | Dany Weer | Gerdien.Cammeraat@ciellos.com
DevOps | Dev - Developer | Functional Design | Microsoft A&A - Bill.com | Maksym Tkachuk | inna.lobanova@ciellos.com
| SE - System Engineer / DevOps | Integration Design | Aptean | Andrii Soroka | daryn.terlesky@ciellos.com
| QA - Testing/QA | Development |  | Inida Noga
|  | Testing |  | Sergiy Myronov-Kopysov
Training
Implementation
DevOps